## Executive Dashboard
CORRESPONDENT GATE - UPDATED PROOF-TO-ARTIFACT EVIDENCE MATRIX
MVP proof is separated from designed Stage 5-6 recommendations. The team has not deeply analyzed or implemented the proposed Power Platform production architecture.
Verified / reported metric | Value |  | Evidence class | Meaning | Can claim | Cannot claim | Primary source
Expanded requirements | 45 |  | EXECUTED | Workflow or command ran with observed output | Demonstrated behavior | Production deployment | Test evaluations
Validator checks | 17 |  | VERIFIED ARTIFACT | Artifact was inspected | Artifact content exists | Every described control executed | Registered files
Canonical source records | 201 |  | REPORTED EVIDENCE | Earlier project record reports the result | Reported project evidence | Current retest without logs | Requirements/summaries
Final integrated test cases | 20 |  | USER-DECLARED | Team supplied process context | Team process record | Independent telemetry | Team statements
Official residual score | 49.97 |  | ESTIMATE | Engineering range | Planning estimate | Billing or exact tokens | Token analysis
Official band | High |  | DESIGNED / NOT TEAM-VALIDATED | Target-state document drafted | Strategy exists for evaluation | Expertise, deployment, testing, SLOs, operations | Stage 5-6 artifacts
Stage 5 readiness | DESIGNED ONLY |  | OPEN | Known incomplete area | Gap is disclosed | Completion | Requirements / Stage 5-6
Stage 6 operations | DESIGNED ONLY
NEW CORRECTED EVIDENCE SECTIONS
Section | Scope | Rows | Strongest executed proof | Evidence gap | Panel use | Status | Sheet
Intake Evidence | Copilot Intake Analyzer plus parser/source-register builder, validator, extract-gate1-packet.ps1, Gate 1 review artifacts and handoff | 7 | 201 canonical fields; 17 checks; fail-closed validation and corrected handoff | Actual intake source files/output packages should be retained and shown | Explain Agent versus deterministic intake boundary | CORRECTED V2 | Intake Evidence
Scoring Evidence | resolve, admission, mapping, scoring, orchestration, configuration, inputs/outputs and tests | 13 | resolve -> READY/AUTHORISED -> 64.00 -> 0.7807 -> 49.97 High -> Gate 3 | Raw code/config/test logs still needed for strongest proof | Show complete Scoring Engine folder and execution chain | CORRECTED V2 | Scoring Evidence

## Proof Matrix
ID | Lifecycle Lens | Claim / Control | Artifact Evidence | Evidence Class | Observed / Proposed Result | Current Status | Gap / Caveat | Presentation Language | Source
P-001 | DISCOVER | Vendor-risk framing changed to correspondent banking | Derivation summary | VERIFIED ARTIFACT | Research-backed scope correction | COMPLETE | Not a formal discovery phase | Scope was corrected after source review | Executive / lifecycle docs
P-002 | DEFINE | Brief expanded into requirements | Expanded Requirements | VERIFIED ARTIFACT | 45 requirements with status and open items | COMPLETE | Some policy decisions remain open | Requirements were documented retrospectively | Expanded Requirements
P-003 | DESIGN | Agent/code/human separation | Agent instructions and summaries | VERIFIED ARTIFACT | AI interprets/drafts; code validates/scores; humans decide | COMPLETE FOR MVP | Production design not implemented | MVP control architecture was designed | Executive summaries
P-004 | BUILD | Validator and source register | Validator evidence | EXECUTED | 17 checks; 201 canonical records reported | PASS / REPORTED | Keep raw outputs available | Validator passed in recorded execution | Audit trail
P-005 | TEST | Incomplete evidence fails closed | Final evaluation TC-01/06 | EXECUTED | RETURN_FOR_CORRECTION / NOT_AUTHORISED | PASS | Synthetic case | Negative paths were demonstrated | Batch 2
P-006 | TEST | Integrated positive path | Batch 2 final evaluation | EXECUTED | READY, AUTHORISED, 49.97 High, Gate 3 admitted | PASS | Gate 3 decision blank | Integrated High path passed | Batch 2
P-007 | TEST | Broader deterministic suite | Requirements/internal summary | REPORTED EVIDENCE | 65 tests and 500 byte-identical runs reported | REPORTED | Not re-executed in final Batch 2 | Earlier project evidence reports these results | Requirements / internal summary
P-008 | REVIEW | Human Gates 1-3 preserve authority | Decision artifacts and Gate 3 packet | EXECUTED / INSPECTED | Gate 3 decision remained blank | PASS | Synthetic decisions | Human authority boundary demonstrated | Batch 2
P-009 | IMPROVE | Contract defects corrected and retested | Defect trail | EXECUTED | PowerShell/Node array and Gate 1 JSON fixes passed | PASS AFTER FIX | Shared schemas recommended | Failure, correction and recovery are evidenced | Batch 2
P-010 | MAINTAIN | Operational token workflow estimated | Token analysis | ESTIMATE | 145k-250k operational workflow | ESTIMATED | Not telemetry | Use estimated model tokens processed | Token Analysis
P-011 | DEPLOYMENT 5 | Power Apps/Dataverse/Copilot Studio target architecture | Production Readiness Strategy | DESIGNED / NOT TEAM-VALIDATED | Theoretical production architecture and workflow | DRAFT STRATEGY | Team has general Power Apps idea only; no deep analysis or expertise claim | A target-state strategy was drafted for evaluation | Stage 5
P-012 | DEPLOYMENT 5 | Token optimization target | Production Readiness Strategy | DESIGNED / NOT TEAM-VALIDATED | Deterministic parsing, compact contracts, canonical facts, templates, routing, budgets | PROPOSED | 40-65% target is unproven until pilot telemetry | Optimization recommendations require pilot proof | Stage 5
P-013 | DEPLOYMENT 5 | Go-live path | Production Readiness Strategy | DESIGNED / NOT TEAM-VALIDATED | Governance -> foundation -> build -> shadow -> limited -> GA -> scale | PROPOSED | No environment, licensing, pipeline, pilot or deployment exists | A phased go-live path is proposed | Stage 5
P-014 | OPERATIONS 6 | Monitoring and observability | Operations Plan | DESIGNED / NOT TEAM-VALIDATED | Copilot Studio, Power Platform, App Insights, Azure Monitor, Power BI model | PROPOSED | No production telemetry or dashboards | An observability model is proposed | Stage 6
P-015 | OPERATIONS 6 | SLOs, alerts and incidents | Operations Plan | DESIGNED / NOT TEAM-VALIDATED | Pilot SLO candidates, severity matrix, runbooks and incident flow | PROPOSED | No SLO approved or measured; no runbook exercised | Candidate controls, not operations evidence | Stage 6
P-016 | OPERATIONS 6 | Continuous improvement | Operations Plan | DESIGNED / NOT TEAM-VALIDATED | Daily/weekly, biweekly, monthly, quarterly and annual review cadence | PROPOSED | Team has not adopted this cadence | A future improvement cadence is proposed | Stage 6
P-017 | HARNESS | Copilot Agent (Flynn) role | Team process record | USER-DECLARED | Solutions Architect role player used by a QA team member in Consulting Project; contributed to hackathon | RECORDED | No platform usage export | Describe as team-reported role | User clarification
P-018 | HARNESS | Claude Agent role | Team process record | USER-DECLARED | Created specifically to help design/build hackathon; reciprocal review with Flynn | RECORDED | No Claude transcript/telemetry registered | Describe as team-reported role | User clarification
P-019 | HARNESS | Total project token use | Updated estimate | ESTIMATE | 335k-700k; planning 520k; sensitivity 250k-950k | ESTIMATED | Covers both Agents, all prompts and known artifacts including current session; not billing telemetry | Use planning estimate with range and caveat | Derived from token analysis plus artifact sessions
P-020 | GAP | Production readiness and scale | Stage 5-6 plus requirements | OPEN | Not implemented, tested or operated | OPEN | No expertise or production claim | Stage 5-6 close the documentation gap, not the implementation gap | All core artifacts

## Stage 5-6 Strategy
Area | Stage 5 Proposed Strategy | Stage 6 Proposed Operations | Evidence Status | Team Position
Experience | Power Apps model-driven app | Operations cockpit and support views | DESIGNED / NOT TEAM-VALIDATED | General idea only
Data | Dataverse plus controlled document store | Capacity, audit, retention and data-quality monitoring | DESIGNED / NOT TEAM-VALIDATED | No implementation
Agents | Copilot Studio Intake and Memo Agents | Monitor Agent health, grounding, guardrails and cost | DESIGNED / NOT TEAM-VALIDATED | Requires redesign/evals
Workflow | Power Automate; Azure orchestration where needed | Flow health, retries, backlog, dead letters and aging | DESIGNED / NOT TEAM-VALIDATED | No flows built
Deterministic services | Azure-hosted Node.js validator/scoring APIs | Application Insights, version drift and invariant checks | DESIGNED / NOT TEAM-VALIDATED | Conceptual migration
Reporting | Power BI dashboards | Business, risk, Agent, operations and cost dashboards | DESIGNED / NOT TEAM-VALIDATED | No dashboards
Deployment | Managed solutions, pipelines, shadow pilot, limited rollout | Release health, rollback, incidents and continuous improvement | DESIGNED / NOT TEAM-VALIDATED | No go-live activity

## Token Estimate
Work category | Low | High | Planning note | Telemetry caveat
Original two-Agent solution workflow | 145000 | 250000 | 200000 | Existing operational analysis
Requirements/research/architecture/prompts/design | 90000 | 200000 | 145000 | Both Agents; exact Claude and Copilot telemetry unavailable
QA/defect correction/retest/evaluation | 55000 | 140000 | 90000 | Multiple long-context iterations
All artifact creation and revision sessions | 45000 | 110000 | 85000 | Includes Stage 5, Stage 6, recreated artifacts and current session
Estimated total project | 335000 | 700000 | 520000 | Model tokens processed estimate
Sensitivity envelope | 250000 | 950000 | 520000 | Hidden prompts, retrieval, retries, tokenizer differences, compaction/reuse

## Source Register
ID | Artifact | Role | Evidence qualification
S1 | Consolidated Executive Summary - Complete | Executive narrative and claims | Updated with designed Stage 5-6 and new token estimate
S2 | Project Lifecycle Evidence Record - Complete | Detailed retrospective lifecycle evidence | No formal SDLC claim
S3 | Production Readiness Strategy - Deployment Stage 5 | Target architecture, workflow, token optimization and go-live | Designed only; not deeply analyzed or implemented
S4 | Operations, Monitoring and Continuous Improvement Plan | Target operating model and observability | Designed only; no production telemetry or adopted SLO
S5 | Test Evaluation Notes and Audit Trail | Earlier validator and blocked-state evidence | Executed / artifact evidence
S6 | Batch 2 final evaluation records | Correction, rerun, score and Gate 3 admission | Latest integrated positive-path evidence
S7 | Token Analysis | Operational workflow token ranges | Estimate, not billing telemetry
S8 | Team clarifications | Agent roles, informal work style, Power Apps general direction | User-declared process context
ADDITIONAL EXECUTABLE-HARNESS EVIDENCE
X1 | Copilot Intake Analyzer instructions and semantic outputs | Provisional semantic analysis and Draft Gate 1 evidence | Agent artifact; no scoring authority
X2 | Workbook parser / source-register builder and generated register | Canonical intake evidence | 201 records reported; register actual files when available
X3 | Validator source and validation report | 17 contract checks and final package PASS | Intake-side deterministic evidence
X4 | extract-gate1-packet.ps1 and execution log | Intake-to-scoring extraction and normalization | File is under Intake Analyzer/Validator folder; defect and fix executed
X5 | resolve.mjs, resolve.test.mjs, and gate1-decision.json | Scoring Engine decision-resolution step | Corrected ownership: Scoring Engine
X6 | admission.mjs and admission.test.mjs | Scoring Engine authorization/refusal | READY/AUTHORISED path and blockers
X7 | mapper.mjs, mapper.test.mjs, mapping.rules.v1.1.json | Scoring Engine mapping | Final F1-F6/C1-C4 trace; synthetic model
X8 | scoring.mjs, scoring.test.mjs, weights.v0.1.json, scoring_output.json | Official deterministic calculation | 64.00 / 0.7807 / 49.97 High
X9 | fullRun.mjs and execution log | Scoring Engine orchestration | Integrated run; retain raw console/log
X10 | README.md plus retained input/output JSON set | Scoring Engine package evidence | Folder view supplied; contents not all independently opened

## Intake Evidence
INTAKE ANALYSIS AND DETERMINISTIC INTAKE PIPELINE EVIDENCE
Boundary correction: the Copilot Intake Analyzer is an Agent. The intake-side deterministic components are the workbook parser/source-register builder, package validator, and extract-gate1-packet.ps1. resolve.mjs belongs to the Scoring Engine and is documented on the Scoring Evidence sheet.
ID | Component / Artifact | Technology / Type | Purpose | Primary Evidence | Evidence Class | Observed / Reported Result | Current Status | Gap / Caveat | Source Record
I-001 | Copilot Intake Analyzer | Copilot Agent | Interpret controlled intake documents; propose material facts, evidence states, contradictions, indicators, exceptions, hard-exclusion candidates, and Draft Gate 1 material. | Agent instructions; semantic Part 1/Part 2 outputs; Draft Gate 1 package described in registered summaries and evaluation notes. | VERIFIED ARTIFACT / REPORTED EVIDENCE | Produced provisional review material without official scoring or approval. | MVP ARTIFACT EVIDENCE | Agent package itself should be shown to panel if available; current matrix relies on registered summaries/evaluation records. | Executive summaries; lifecycle record; test notes
I-002 | Workbook parser / source-register builder | Deterministic parser utility | Read original workbooks and create canonical field-level source records with IDs, locations, and normalized values. | Validator audit trail and recorded source-register result. | EXECUTED / REPORTED EVIDENCE | 201 canonical source-register records recorded. | PASS / REPORTED | Actual parser source file and generated register are not separately registered in this workbook. | Test Evaluation Notes and Audit Trail v1.0.0
I-003 | Deterministic package validator | Node.js deterministic component | Validate JSON/package contract, identity, uniqueness, references, mappings, counts, versions, blank human fields, and prohibited Agent outputs. | Validator report and audit trail. | EXECUTED | 17 checks recorded as passing in earlier execution; final positive package also recorded PASS. | PASS | Keep the raw validator report and source file available for panel inspection. | Audit trail; Batch 2 final evaluation
I-004 | extract-gate1-packet.ps1 | PowerShell script | Extract and normalize Gate 1 candidates from the validated package for delivery to the Scoring Engine. | Batch 2 defect and retest record; uploaded folder view places the script under 01_Intake Analyzer / Correspondent Gate Validator. | EXECUTED | Initial wrapper-object/array mismatch caused a Node.js TypeError; extractor was corrected to normalize the candidates array; retest passed. | PASS AFTER FIX | The script file itself is not embedded in this matrix; evidence is the execution/defect trail and folder placement supplied by the team. | Batch 2 final evaluation; uploaded folder image
I-005 | Gate 1 review packet / handoff artifact | Review packet / JSON handoff | Carry validated intake facts, indicators, exceptions, and hard-exclusion candidates to human Gate 1 and then to the Scoring Engine. | draft-gate1-packet.json, deterministic-validation-report.json, exhaustive-source-register.json shown in the uploaded scoring-engine folder view; execution records in Batch 2. | VERIFIED ARTIFACT / EXECUTED HANDOFF | Validated intake artifacts were passed to Gate 1 and used by the Scoring Engine after correction. | PASS AFTER FIX | Human decisions are applied inside the Scoring Engine by resolve.mjs; they are not applied by the intake pipeline. | Uploaded folder image; Batch 2 final evaluation
I-006 | Intake-to-scoring handoff contract | Versioned JSON/package contract | Transmit validated intake artifacts and Gate 1 review inputs into the Scoring Engine without allowing the Intake Agent to authorize or calculate scoring. | Package validation status, Gate 1 packet, source register, validator report, scoring-engine input artifacts, and defect trail. | EXECUTED | Unresolved exclusions and incomplete evidence blocked authorization; corrected artifacts proceeded through the Scoring Engine. | PASS | Shared JSON Schema across PowerShell and Node.js remains a recommended improvement. | Audit trail; Batch 2 final evaluation; uploaded folder images
I-007 | Negative intake controls | Evaluation cases | Prove missing, incomplete, conflicting, wrongly shaped, or unresolved intake data fails closed before official scoring. | TC-01, TC-02, TC-05, TC-06, and correction/recovery cases. | EXECUTED | RETURN_FOR_CORRECTION, mapping conflict, TypeError, and HARD_EXCLUSION_UNRESOLVED states observed before correction. | PASS | Synthetic inputs; not production-volume or adversarial document testing. | Batch 2 final evaluation

## Scoring Evidence
DETERMINISTIC SCORING ENGINE AND EXECUTION EVIDENCE
Corrected ownership: resolve.mjs is part of the Scoring Engine, alongside admission.mjs, mapper.mjs, scoring.mjs, and fullRun.mjs. The uploaded folder view shows these modules and their tests together under 02_Scoring_Engine / _Scoring Engine / correspondent-gate.
ID | Component / Artifact | Technology / Type | Purpose | Primary Evidence | Evidence Class | Observed / Reported Result | Current Status | Gap / Caveat | Source Record
S-001 | resolve.mjs | Node.js Scoring Engine module | Apply human Gate 1 decisions to facts, indicators, exceptions, and hard-exclusion candidates before admission. | Uploaded scoring-engine folder view; runtime-source inspection; corrected gate1-decision.json; resolution logs and Batch 2 retest. | EXECUTED | Incorrect nesting/field names first failed; corrected top-level arrays and runtime field names applied HEX-0002 and HEX-0003 as NOT_TRIGGERED. | PASS AFTER FIX | Register resolve.mjs, resolve.test.mjs, gate1-decision.json, and raw resolution log as retained artifacts. | Uploaded scoring-engine folder image; Batch 2 correction/retest
S-002 | resolve.test.mjs | Node.js Scoring Engine test | Test Gate 1 decision application and resolution behavior. | File is visible beside resolve.mjs in the uploaded scoring-engine folder. Test behavior is discussed in registered evaluation records. | VERIFIED FILE PRESENCE / REPORTED EVIDENCE | Test file exists in the Scoring Engine folder; resolution behavior passed after correction. | MVP ARTIFACT EVIDENCE | The test source and direct execution log were not uploaded separately in this conversation. | Uploaded scoring-engine folder image; Batch 2
S-003 | admission.mjs | Node.js Scoring Engine module | Check package status, evidence completeness, resolved Gate 1 decisions, exclusions, versions, mappings, and required anchors before scoring. | Uploaded scoring-engine folder view; admission output; negative/positive execution logs described in Batch 2. | EXECUTED | Blocked with unresolved exclusions/incomplete inputs; later returned READY and AUTHORISED with no open blockers. | PASS | Retain admission.mjs, admission.test.mjs, and raw logs beside the matrix. | Uploaded folder image; Batch 2 TC-06 to TC-11
S-004 | mapper.mjs | Node.js Scoring Engine module | Map accepted source facts through versioned mapping rules into inherent factors F1-F6 and control domains C1-C4. | Uploaded scoring-engine folder view; mapping.rules.v1.1.json; factor trace; mapping defect/correction history. | EXECUTED | Final trace used F1-F6 anchors and source IDs, including F5 from SRC-CBDDQ-19 and F6 from SRC-SCOPE-S23. | PASS AFTER FIX | Synthetic mapping is not an approved production model. | Uploaded folder image; Batch 2 final scoring trace
S-005 | scoring.mjs | Node.js Scoring Engine module | Calculate weighted inherent risk, combined control multiplier, residual floor, official residual score, band, and routing. | Uploaded scoring-engine folder view; weights.v0.1.json; scoring_output.json values and arithmetic reconciliation. | EXECUTED | Inherent 64.00; control multiplier 0.7807; residual 49.97; floor 12.80 not applied; High; Committee at Gate 3. | PASS | Retain scoring.mjs, scoring.test.mjs, weights, output JSON, and config hash. | Uploaded folder image; Batch 2 TC-12 to TC-15
S-006 | fullRun.mjs | Node.js Scoring Engine orchestration module | Run resolve, admission, mapping, and scoring sequence and emit final case/run outputs. | Uploaded scoring-engine folder view; corrected end-to-end run; final evaluation record. | EXECUTED / REPORTED EVIDENCE | CG-CASE-HP-002 / CG-RUN-HP-002 reached official scoring and Gate 3 admission. | PASS | Preserve raw console/execution log for strongest proof. | Uploaded folder image; Batch 2 integrated evaluation
S-007 | Scoring Engine configuration | JSON configuration artifacts | Define mapping rules and weights separately from code. | mapping.rules.v1.1.json and weights.v0.1.json visible in the uploaded folder; version-conflict tests and scoring trace. | VERIFIED FILE PRESENCE / REPORTED EVIDENCE | Configuration files exist and version mismatches blocked progression in testing. | MVP ARTIFACT EVIDENCE | Exact configuration content was not uploaded for independent inspection here. | Uploaded folder image; Expanded Requirements; Batch 2
S-008 | Scoring Engine inputs and retained outputs | JSON evidence artifacts | Provide validated intake, Gate 1 decision, source register, validation report, and official scoring result to the engine and downstream gates. | scoring_output.json, draft-gate1-packet.json, deterministic-validation-report.json, exhaustive-source-register.json, and gate1-decision.json visible in the uploaded scoring-engine folder. | VERIFIED FILE PRESENCE / EXECUTED WORKFLOW | Folder contains the principal input/output evidence set used by the final run. | PASS / ARTIFACT PRESENCE | File contents were not independently opened in this turn; execution results remain grounded in registered evaluation records. | Uploaded scoring-engine folder image; Batch 2
S-009 | Factor calculation reconciliation | Independent arithmetic check | Verify anchors, weights, contributions, multiplier, residual, floor, band, and routing. | TC-12 through TC-15. | EXECUTED | 12 + 15 + 6 + 0 + 25 + 6 = 64.00; 0.94^4 = 0.7807 rounded; 64.00 x 0.7807 = 49.97. | PASS | High-band threshold interval was not embedded in the supplied scoring output, per evaluation caveat. | Batch 2 arithmetic cases
S-010 | Negative scoring controls | Evaluation cases | Prove scoring refuses incomplete evidence, unresolved exclusions, version mismatch, missing anchors, or unauthorized state. | Earlier blocked-state notes and final Batch 2 negative tests. | EXECUTED | NOT_AUTHORISED and correction states occurred before the successful run. | PASS | Production security, concurrency, tamper, and scale tests remain open. | Audit trail; Batch 2
S-011 | Automated module tests | Node.js test files | Test resolve, admission, mapping, and scoring modules. | resolve.test.mjs, admission.test.mjs, mapper.test.mjs, and scoring.test.mjs visible in the uploaded scoring-engine folder. | VERIFIED FILE PRESENCE / REPORTED EVIDENCE | Module-level test files exist; broader suite of 65 tests is reported in earlier project evidence. | REPORTED / FILE PRESENCE | Raw test output was not uploaded separately. | Uploaded folder image; Expanded Requirements; Internal summary
S-012 | 500-run repeatability test | Determinism evidence claim | Prove identical input/version yields byte-identical output repeatedly. | Expanded Requirements and Internal summary. | REPORTED EVIDENCE | 500 repeated executions with byte-identical output reported. | REPORTED | Raw repeatability log is not registered in this matrix. | Expanded Requirements; Internal summary
S-013 | Half-up rounding and residual-floor tests | Numerical invariant tests | Confirm explicit rounding and 20% residual-risk floor behavior. | Expanded Requirements, Internal summary, and final run floor trace. | EXECUTED / REPORTED EVIDENCE | 2.675 -> 2.68 reported; final run calculated floor 12.80 and correctly did not apply it. | PASS / REPORTED | Separate raw boundary/floor-binding outputs should be retained if presented. | Expanded Requirements; Batch 2